## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | TalkIt
Project Manager | Dan.Badris
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Severity | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | Severity | PM | Lifecycle Phase
1 | 2017-10-01 |  | Messages are duplicately posted | Planning | Requirement | Meduim | Low |  | 2017-10-01 | 2017-10-15 | Closed | NA | 2017-10-05 |  | this is happeing due to the local server installation and testing.. it wont be occure in production | New
2 | 2017-10-14 | Dan.Badris | The chat application accepts executable HTML/JavaScript code injection which severely threatens user security as the code might intercept other sessions, impact traffic or execute harmful spyware | Closing | Testing | High | High |  | 2017-10-15 | 2017-10-30 | In Progress | a restriction on the user input will be applied to refine user inputs and assure high level of security |  | 5 days |  | Under Review | Critical | Critical | Opportunity Assessment | Opportunity Assessment
3 | 2017-11-05 | Jash Bhankharia | In Create New Team part, application accept empty string on Team Name field. Team name cannot be empty.This cause a error. | Closing | Testing | Low | Low |  | 2017-05-11 | 2017-05-11 | Completed | a restriction on the user input has been applied to refine user inputs | 20/11/2017 | 10 days |  | In Progress | High | High | Initiating | Concept
4 | 2017-11-05 | Asli Terzioglu | In chat application,two chat teams can be created with the same name. | Closing | Testing | Low | Low |  | 2017-05-11 | 2017-05-11 | Completed |  | 2017-05-11 | 2017-05-11 |  | Completed | Medium | Medium | Planning | Requirements
5 | 2017-12-01 | Eman Zayer | Login-Coomunication tool- vedio Stream -'Cannot Set Description' - Network Issue - Different Network will work | Closing | Testing | High | High | Dan Badris | 2017-12-01 | 2017-12-02 | Completed | Security workaround | 2017-12-02 | 1 day | Connection is blocking calls |  | Low | Low | Executing/Controlling | Design
6 | [18 empty] | Closing | Development
7 | [19 empty] | Testing
8 | [19 empty] | Documentation and Training
9 | [19 empty] | Deployment
10 | [19 empty] | Post-Deployment
11
12
13
14
15
16
17
18
Note on E9: Choose from the drop down box.
Note on F9: Choose from the drop down box.
Note on G9: Choose from the drop down list
Note on H9: Choose from the drop down list
Note on L9: Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
C = Critical (Tremendous, the whole application won’t work unless it is resolved) should be fixed immediately.
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Severity | The Severity denotes the implication of the defect on the project performance
C = Critical / Show Stopper (A defect that completely hampers or blocks testing of the product or any feature. To be solved immediately)
H = Major / High (functionalities are running grossly away from the expectations or not doing what it supposed to)
M = Moderate / Normal (A product or application doesn’t meet certain criteria or exhibits some abnormal behavior, but the entire functionality is still working fine)
L = Minor / Low (A bug does not have any impact on the functionality but it is still a valid defect and should be tackled)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).

## Test Cases
Test Type | Test case ID | New or old | Test items: (what do you test ) | Test priority (high/medium/low) | Dependencies (to other test case/requirement if any): | Preconditions: (if any) | input data | Test steps: | Postconditions: | Expected output | Actual output: | Pass or Fail: | Bug id/link: | Additional notes
Manual | 1.1.1 | Old | Create User | Low | Environment should be activated | 1. Corporate Email account should be used for rigestration 2. Enter a password of 6 to 20 characters which contain at least one numeric digit, one uppercase, one lowercase letter | First name: Eman Last name: Zayer Email: Zayereh@bu.ed Username: Zayereh Password: Eman.123456 Password confirmation:Eman.123456 | 1. Open the URL: http://3blueprints.com/signin?next=/communication/ 2. Click on "I want to Register" or "Sign Up" in the screen upper right corner 3. Enter the input detailes 2. Click "Register" | user created | Registration Complete! | Registration Complete! | Pass | NA
Manual | 1.2.1 | Fix | Create Chat Team | Low | User is logged in | Team name should not be Empty | Team name: " " | 1. New Team name is empty 2. Save | NA | Empty Team Name should not be accepted | Empty Team Name accepted | Failed | 3
Manual | 1.2.2 | Fix | Create Chat Team | Low | User is logged in | Team name should not be Empty | Team name: CS763f17 | 1.Create New Team 2. Enter Team Name 3. Save | New Team is listed in the left menue | New Team is created |  | Pass | 3
Manual | 1.3.1 | Old | Text Chat | High | User is logged in | Room Is selected | Conversation Text | 1. Place the Cursor in the message typing field 2. Enter or click Send Message Icon | Entered Message is sent and apprears in the chat area | Other Chat room Participants receive the message | Other Chat room Participants receive the message | Pass | NA
Manual | 1.4.1 | New | Video Chatting | High | User is logged in | Camera/Microphone are enabled in the browser sercurity settings | - | Click on the Video Chat Icon | Video Chat Started | Video Chat screen appears on the chat room Camera is started | Video Chat screen appears on the chat room Camera is started | Pass | NA
Manual | 1.5.1 | New | File Sharing via Google Doc -Upload | High | user is logged in the Communication tool Chat room | Logged into google drive | File to be picked up ready for sharing | 1. Click Google Drive Icon 2. Select Upload File from the menu 3. Sign in to google account 4. Click on "Select File" 5. Brows Then select file from the local drives 6. Upload | Google Sign In Screen Pops up | File is uploaded and shared via google Drive | File has been uploaded and shared via google Drive | Pass | NA
Manual | 1.5.2 | New | File Sharing via Google Doc -Download | High | user is logged in the Communication tool Chat room | Logged into google drive | File to be downloaded from google drive | 1. Click Google Drive Icon 2. Select Download File from the menu 3. Sign in to google account 4. Select a specifc File to be downloaded then Enter | Google Sign In Screen Pops up | File is downloaded from google Drive | File has been downloaded from google Drive | Pass | NA
Manual | 1.6.1 | New | Chat scripting messages - Santitize input messages to remove HTML | High | user is logged in the Communication tool Chat room | NA | message with exexutable code | 1. In the Chat room type the text (1. <!DOCTYPE html>) 2.Enter/Send | Code is automatically eliminated from the message | only "1." is received | code is exuted over the chat room | Failed | 1
Manual | 1.6.2 | New | Chat scripting messages - Santitize input messages to remove HTML | High | user is logged in the Communication tool Chat room | NA | message with exexutable code | 1. In the Chat room type the text (1. <!DOCTYPE html>) 2.Enter/Send | Code is automatically eliminated from the message | only "1." is received | code is eliminated and the pain text is sent | Pass | 1
Manual | 1.7.1 | Fix | Chat Room File Sharing | Meduim | user is logged in the Communication tool Chat room | NA | file of any type to be sent through the conversation | 1. In the Chat room cleck on the "Send File" 2. "Upload Files" Pop-up screen should show up 3. Type a "Display Name:" 4. Browes and select the dignated file from the local driver 5. Upload | File is sent over the chat room | File is shared over the chat room | File is shared over the chat room | Pass
Manual | 1.8.1 | New | Tool Bar menue | Meduim | user is logged in the Communication tool Chat room | NA | - | 1. from the chat Room upper right corner click on userID 2. Manage profile/Logout | dropdown menu appears to the user | user can navigate throughot the added toolbar' | user navigated throughot the added toolbar' | Pass
Manual | 1.9.1 | New | Login-Coomunication tool- vedio Stream -'Cannot Set Description' - Network Issue - Different Network will work | High | user is logged in the Communication tool Chat room | intenet connection is not blocking video/audio call | Running from server | 1. Log in to chat Room 2. Start vedio Chatting | internet connection allows the media sharing | media connectivity started | connection failed | Failed | 5
Manual | 1.9.2 | New | Connection to the media server / Security | High | user is logged in the Communication tool Chat room | intenet connection is not blocking video/audio call | Running from server | 1. Log in to chat Room 2. Start vedio Chatting | Video Chat Started | media connectivity started | media connectivity started | Pass | 5
Manual | 1.10.1 | New | Message duplication | High | user is logged in the Communication tool Chat room | Test from server | Text message sent through local server | 1. Log in to chat Room 2. send text message | - | only one copy of the message to be sent over the chat room | sent message received twice | Pass | 3
Manual | 1.11.1 | New | Change password | Meduim | user is logged in the Communication tool Chat room | Old Password is known to the user | Original Password: New Password: Confirm Password: | 1. From the upper right corner, Click on the user name 2. From the Drop down menue select "Change Password" 3. Enter old/New password 2.Click "Confirm Change & Logout" | Password is updated | Password is changed successfully | Password has been changed successfully | Pass
Selenium Test |  | New | Upload file to chat room via Google Drive | high
Selenium Test |  | New | Download file to chat room via Google Drive | high
Selenium Test |  | New | Check video chat funcionality | high
Selenium Test |  | Old | User login to communication page | high |  |  | username, password
Selenium Test |  | Old | Create chat team | medium |  | registered user | Team name | 1.Login user 2.Click "Create New Teams " button 3.Add team name 4.Click "save" button 5.Check whether new team is created |  | the new team name will show in"Chatting Room" list | Same as expected | Pass
Selenium Test |  | New | Edit Team Name | low |  | registered user, team which created before | new team name for edit | 1.Login user 2.Click "Create New Teams " button 3.Add team name 4.Click "save" button 5.Click "Options" button and than "Edit Team" 6.Edit team name 7.Check whether team name is edited | If team name does not change, there is no diffrence on Team list. Editted name should not be empty. | the edited team name will show in "Chatting Room" list | Same as expected | Pass
Selenium Test |  | New | Check system accept to unsanitized message to chat room | high |  | user login into system, team which created before | message for input box | 1.Enter a created team 2.Send a message which is unsanitized like Html code to this team 3.Check is message rendered as text |  | message will show in message list as a text | Same as expected | Pass
Selenium Test |  | Old | Dialog between two user in the chat room | high |  | two user who login successfully to the system created team | messages for input box | 1.First user enter a created team 2.Send a message to this team 3.Second user also sent a message to this team 4.Check whether messages is sent and users can see both messages |  | both messages will show in message list in the same team | Same as expected | Pass