## Contribution
StudentName | RequirementAnalysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management
Dan Budris | Created user stories for video chat application, help documentation, and bug fixing to pivotal tracker, with acceptance criteria and detalied task breakdowns | Created draft of design documentaiton, incorporating class diagrams from various team members and information about the existing architecture from the previous semesters. |  | Created initial outline for presentations in iterataion on 0 and 1; developed the content for the configuration managment slides in iteration 0 presentation; wrote slides and presentation content for CSX (current state of bugs, slide 9) and current state of the application slides (2-7) in presentation 1. | committed code which: added tooltips to comm app added help icon (unmerged) added div area with flexbox where we can later add video (unmerged) stopgap fix for cross-site scripting (regex which strips html tags) start for real fix to XSS using express api sanitizer dockerfile which codifies the deployment off the application in code and configurations which allow for automated docker deployments | Manually tested the chat applicaiton with various input types leading to discovery of XSS vulnerability | Worked with team members to set up and install Git and learn github; developed and implemented an automated docker build which is used by myself and a couple other team members as a development enviornment (see https://hub.docker.com/r/danbudris/bu_met_cs673/ for information about the automated build; it builds when code is committed to github); worked with Mithil to develop git branching strategy and commit standards | Attended and generally facilitated team 4 meetings. Set up integration between github and slack. Respond to team members and post updates regularly on slack. Worked with team members and co-lead George on team direction and strategy. Provided assistance and help to other team members as needed. Reviewed and merged code of others on Github
George Goddard | - Added 3 Google Drive Integration user stories for upload, download, and share files. - Added users stories for Google Picker implementation |  |  | - Contributed to the slides for presentations in iteration-0, iterations-1, and iteration-3. - Presented in iteration-0 and interation-3. - Drove planning and delegation for iteration-2 presentation. | - Checked in code to create the Google Drive button and the associated drop down menu. I had to modify the Emoticons html so that it was wrapped in a button group. Otherwise both adjacent dropdown menus had the same behavior. - Contributed a new django sub-project to the communication tool for oauth2-authentication. Completed backend implementation for Google Drive file download. Did a light refactoring on all existing python classes in the django portion of the communication tool. - Implemented Google Picker functionality in the frontend - Implemented Google Drive file upload functionality in the frontend - Partially implemented Google Drive file download in the frontend. Having issues with authentication. | - Between iteration-0 and iteration-1, downloaded all the necessary testing packages to my development vm. The python tests had a lot of testing files specified which didn't exist, so I had to remove those. I was eventually able to run both the unit tests and selenium tests. Over 50 tests passed, one test failed, and there were 10 errors regarding trying to use a port that was already in use. I still need to troubleshoot that. - Provided assistance in development of unit and selenium tests to other teammates | - With Jash, I created an image of my development vm in iteration-0 so that it could be used by any interested team members. | - I am consistently on Slack. I post updates, checkins, recommended documentation, information about meetings, responses to questions, etc. I have written the weekly meeting minutes twice since the project started. I am the back up leader of the team and the leader of the Google Drive Integration sub-team. I have helped team members troubleshoot their development environments, made corrective recommendations on GitHub, and helped with implementation questions.
Jash Bhankharia | Added a user story on pivotal tracker to integrate the toolbar on the communication tool. |  |  | Helped in making and some presentation slides for Iteration 1 and also presented them. Also worked on the bugs and project management slides for the final iteration | Checked in code on development branch to show the demo of WebRTC video chat in iteration 1 presentation. Also wrote code to implement the chat toolbar in communication tool. Fixed the bug where the file upload feature wasn't working and also minor team name validation issues. | Assisted the testing sub team for trying out Unit testing using JavaScript on the front end. | WIth help from George, created a virtual machine image which the team members can use directly. I also updated the readme file to helo the team members with the steps to work with that virtual machine. Assisting the team members with GIT usage whenever required | Active on Slack. Helped some team mebers with using Github and how to commit stuff. In collabaration with Mithil, we suggested to use feature names as branch names on Github for proper management of branches. I have been the leader of sub group 1 which involves all UI related changes required (General changes or changes for other sub groups implementation). Been present in most of the team meetings and have made suggestions on implementation regularly.
Yergali Askarbayev | Added user stories of video chatting on pivotal tracker |  |  | Created pages in presentation for iteration 1 and presented them | commited on featute/videochat_webrtc branch to implement a demo video chat. In addition to this, implemnting the individual texting feature. |  |  | Attending all meating of the team 4 and subteam. Suggesting different ways of the implemention in order to reach as many as features by the end of the semester.
Asli Terzioglu | Added 2 User Story : They are bugs about same team name and empty team name |  | added test summary and introduction part, also added test senarios to Team4_defect_tracking_log.xlsx for selenium tests | In iteration 1, presented and added slides about current bugs and class diagram for communication tool. In final presentation, I presented selenium test part | I commited on bug/sameTeamName branch to fix the bugs in iteration 2. | I committed selenium test cases which is written with python on iteration 3 |  | I attended Team 4 and subgroup meetings and used slack for communication with other team members
Mithil Shah | Added 2 User story about Video Thumbnail and Display name for chat windows. Managed major part of pivotal tracker | Worked on certain documents like managing meetings of minutes and presentation layouts |  | In final presentation, i presented the project metrics section. | I have not yet committed any code under my account on the repository yet. I have been involved more actively in design and architecture part of the implementation. I was involved in pair programming for bug fixes with jash b. | Involved closely in manual testing and learning selenium. With the testing subteams. with asli oindrilla. Directing and designing important test cases. | Worked with team members to set up and get them acquainted with Github. Set up repositiories on their personal machines and explain the use and idea of git. | Attended several meetings and volunteered for extra meeting for sub team work. i have been active on slack & checking the commits on github all time. Managed several presentation related tasks and coordination. Also i have always been involved in
Nitish Gaddam
Shaurya Muttreja |  | Made the system architecture diagrams in SDD document (Class diagram and Use Case diagram). Designed a logo for the communication tool |  | Presented in Interation 2 by explaing the system overview and architecture with the use of the class diagram and use case diagram | I have not produced any code on github yet, since this is my first time using the platform. I am in the process of learning Python-Django as well | Manually tested the registration and admin panel which require the admin to update user permission before the user can create a project |  | Attended several meetings with the whole team and separtely with my subteam as well.
Eman Alzayer | Created User Stories for the project |  | created User Acceptance Criteria and tacking sheets for the project testing | As a QA Manager, expalined and updated the QA and testing requiremnts for the project |  | working in Selinium /Jenkins testing and integration/unit testing | working in Selinium /Jenkins testing and integration/unit testing | attended meetings, communicated on slack with other team members. I check the commits on github to be familier with all codes and updates, meets with my sub group in the biweekly meeting to work on the testing and final presentation, and also follow the contributions made.
Apurva Katagi | Added 3 user stories to the pivotal tracker for organizing messages |  |  | Made slides for presentation in iteration 1 and presented them. | I committed on github for fixing error in the execution commands. I committed to fill the missing information in the documents. Reviewed few commits made and merged to the branches. |  |  | Attended meetings, communicated on slack with team members and with Dan. I check the commits on github, and also follow the contributions made. Took meeting minutes.
Oindrilla Chatterjee | Added user stories call log menu, notification mechanism and video icon enable/disable |  | Created Selenium tests for login and logout test case. Wrote Junit tests for test cases | Presented and compiled Presentation for Iteration 0. Also, Testing module in Presntation for Final Iteration |  | Worked extensively on Regression and Manual testing. Used the Selenium WebDriver testing framework to implement tests for Login, username password entering functionality.Using Django testing suite for Python for tests on Python files |  | Have been actively participating in the team communication. Have been a part of the meetings. Have volunteered thrice in compliation of the minutes of meeting. Have been active on slack. Have worked in collaboartion with co-members to work on specific modules manual and regression testing

## Eman Alzayer
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
Week 1 :09/06 - 09/13 | 5.5 | 2 | 3.5 | 0 - learning 1 - requirement analysis: joined the group. evaluate ideas through scoring matrix 5 - communication/management: roles and responsibilities for each group members | 0.5 | 2 |  |  |  | 3
Week 2 : 9/13 -9/20 | 2.5 | 2 | 0.5 | 5- group members dropped the course.. joined another group and worked .. familirizing with group project
Week 3 :9/20 - 9/27 | 7.5 | 4 | 3.5 | 0- Learning: GitHup-Python 1-Reading and investigating about existing project and used technologies 3- Enviroment setup 5-worked in the presentation and discuess the requirements | 2 | 1.5 | 0.5 |  |  | 3.5
Week 4 : 9/27 - 10/04 | 5 | 3 | 2 | 0 - Understanding code and updating SPPP. 4-Testing and defect log update 6 - Installing the applications on Virtual machine | 1 | 1 |  |  |  |  | 3
Week 5: 10/4 - 10/11 | 7 | 3 | 4 | 1: Created user case stories, tasks to be implemented and acceptance tests for them 3: Working on UI part of the application Testing 5: Coordination in sub group |  | 2 | 2 |  |  | 3
Week 6:10/11 - 10/18 | 9 | 6 | 3 | 0-Automated Testing Environment using : Jenkins 4- Environment Setup using : Jenkins 6-Presentation and SPPP update | 2 | 1 |  |  |  |  | 6

## Mithil Shah
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
Week 1 :09/06 - 09/13 |  | 3 | 4hrs | 0 Review the platform the project idea could be built on. Laid down the coding guidelines. Understood and discussed possible ideas and features on the project going forward and laid down iteration ideas. 0 Set the project up to run and learned the docker version of it. 1 "Set & discussed the version control guidelines. Shared documentation of version control documentation with team " | 2 | 1 | [5 empty] | 4 | 3
Week 2 : 9/13 -9/20 |  | 1 | 4hrs | 0 Explored the application & uncovered bugs. Set up the enviornment. | 4 | [6 empty] | 4 | 4
Week 3 :9/20 - 9/27 |  | 3 | 4hrs | 0 Understood Closely what are possible frameworks for the Video chat application. 1 Started collecting research documents for peer to peer build. Discussed design ideas. | 3 | 1 | [5 empty] | 3 | 4
Week 4 : 9/27 - 10/04 |  | 3 | 3hrs | 1 discussed the possible strategy to build demo app for video chat. Laid down the idea and execution plan | 1 | [6 empty] | 3 | 3
Week 5 : 10/5 - 10/11 |  | 4 | 2 | 3 Researched and implemented the web rtc chat rooms peer sending. Coordinated with team member over video chat relay. |  |  |  | 3 |  |  |  | 3 | 3
Week 6 : 10/12 - 10/18 |  | 3 | 2.5 | 3 Design the peer stream architecture and explored a demo application to understand and incorporate it into 3 blueprints communication tool. Discussed & guided two team members involved in front end implementation and the backend stream management of design for video chat. |  |  |  | 1 |  | 2 |  | 3 | 3
Week 7 : 10/19 - 10/25 | 6 | 3 | 3 | 5 Divided the user stories correctly, Scoped out their requirements and communicated with the team. | [5 empty] | 3 |  | 3 | 3
Week 8 : 10/26 - 11/1 | 4 | 1 | 2 | 5 Understood the analytics and gathered different metrics Prepared for presentation and designed the slides. | [5 empty] | 3 |  | 3 | 3
Week 9 : 11/2 - 11/8 | 3 | 2 | 3 | 5 Laid down the presentation strategy and communicated with the team for correct closing of stories. Generated charts for analytics. | [5 empty] | 3 |  | 3 | 3
Week 10 : 11/9 - 11/15 | 7 | 1 | 2 | 4 Laid down the upfront testing scenarios that need to be addressed. Acquainted myself with selenium, In extra sub team meeting did a small testing walktrhrough with other team members. |  |  |  |  | 3 |  |  | 3 | 3
Week 12 : 11/16 - 11/22 | 5 | 3 | 2 | 3: Started working on the file upload bug. This bug was present in both requirements as well as communication tool. |  |  |  |  | 2 |  |  | 3 | 3
Week 13 : 11/23 - 11/29 |  |  |  | THANKSGIVING BREAK
Week 14 : 11/30 - 12/06 | 4 | 2 | 2 | 3 Continued the bug fix. 5 Communicated the burnouts and other analytics and actions that need to be taken for correct stages. |  |  |  |  | 3 | 1 |  | 3 | 3
Week 15 : 12/07 - 12/13 | 3 | 3 | 3 | 5. Coordinated with team regarding closing of tickets. Prepared the material and strategy for presentation. | [5 empty] | 3 |  |  | 3

## Shaurya Muttreja
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
9/13 - 9/20 |  | 1.5 | 2 | 5-Team collaboration and role discussion for project signup sheet 6-Joined the team | [5 empty] | 1 | 0.5
9/20 - 9/27 |  | 3 | 1.5 | 0-Project ideas were discussed in detail 1-Requirements of technology discussed (Python django, SQLlite) 3-Installed exsisting project locally using docker. (Instruction given from Dan B) 5-Communication on slack channel about potential screen share frameworks(WebRTC) 6-Merge of team 2 and 4 | 1 | 1 |  | 1
9/27 - 10/4 |  | 6 | 1 | 0-Learnt the basic of Git and Github (Small session with team leader) 4-Installed the updated version of the project in a virtual drive, used it for testing application 5-Split up the team into subteams to manage tasks efficiently | 2 |  |  |  | 2 | 2
10/4 - 10/11 |  | 8 | 3 | 0-Learning concepts about django and django plugins. 2-Tried to implement social media authentication for wesbite 4-Tested communication tool for bugs | 2 |  | 4 |  | 2
10/11 - 10/18 |  | 6 | 2 | 0-Tutorials for WebRTC 1- Built user stories about website features 3 -Errors in socialmedia authentication | 1 | 3 |  | 3
10/18 - 10/25 |  | 4 | 2 | 0 - Learnt basic of python 2 - Designed a logo for the communication tool 5 - attended sub team meeting | 3 |  |  |  |  | 1
10/25 - 11/1 |  | 4 | 3 | 1 - Created two user stories with subgroup for the front end development 4 - Manually tested admin panel. Found out that admin permission is required for each user before a project can be created. 5 - Attended team meeting with whole group |  | 2 |  |  | 1 | 1
11/1 - 11/8 |  | 5 | 2 | 1 - Helped with the SDD document and created the class diagram 6 - Gave up with the social media auth because it was giving issues with integration 5 - attended meeting with group and decided to present for interation 2 |  | 2 |  |  |  | 2 | 1
11/8 - 11/15 |  | 4 | 1 | 0 - Learnt how to create use case diagram 1 - created use case diagram for system 5 - attended team meeting
11/15 - 11/22 |  | 6 |  | 0 - Tried to learn more about django framwork by studying existing project 6 - Presented for iteation 2, explained the system architecture with the help of various diagrams | 4 | [5 empty] | 2
11/22 - 11/29 |  | 0 |  | Thanksgiving break. No class or team meeting
11/29 - 12/6

## Oindrilla Chatterjee
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
Week 1 :09/06 - 09/13 | 4 | 0.75 | 3.25 | 0- Learning how to Implement a scoring matrix to fix up a project idea 5- Forming of a Project Group,assignment of roles and responsibilities 6- Brainstorming project ideas ,Discussion of project ideas and finalisation of topic. Analysis of resources required for implementation | 0.5 | [5 empty] | 3.25 | 1. Discussion with the prof. regarding the project idea and scope. 2. Finalise the platform and technologies intended | 5
Week 2 : 9/13 -9/20 | 4.5 | 4 | 0.5 | 0: learning about existing project application , features and requirement analysis and decided a definite scope of Project 5: Joined team 4, assigned roles, discussed merging teams, decided on a project goal | 4 |  |  |  |  | 0.5 |  | 1. Setting up of a Git Repsitory 2. Running test cases on the Existing Application 3. Fill up the SPPP Documentation 4. Create the Iteration 0 Presentation | 2017-08-10
Week 3 :9/20 - 9/27 | 10 | 6.5 | 3.5 | 0: Learning version control using Git, setting up a github repository 2: Designed a work flow, a timeline gantt chart for the coming iterations 5: filling up of the SPPP, Meeting Minutes and Putting up of the Iteration 0 Presentaion slides | 4.5 |  | 2 |  |  | 3.5 |  | 1. Chalk out a Quality Assurance Plan 2. Running test cases | 10
Week 4 : 9/27 - 10/04 | 10 | 8 | 2 | 0: Learning git bash commands. Worked my way through git. Learnt to send pull requests, clone, fork, branch 1: Created user case stories, tasks to be implemented and acceptance tests for them 3: Installed and set up the chat Application 5: Coordination in sub groups
Week 5: 10/04 - 11/04

## Apurva
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | 210 | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
Week1 (09/06/2017- 09/10/2017) | 7 | 3.5 | 3.5 |  | Exploring on different ideas for project. And trying to explore more tools required to have a real world application.
Week 2(09/13-09/17) | 3 | 3 |  |  | Installed the project and reviewed its details and also attended a session to learn more about Git
Week 3(9/20 - 9/27) | 6.5 | 4 | 2.5 |  | 0- spent time to get familiar with the docker | 1Looked into the already existing features and code.Tried to make the changes to make the login page work. |  | Started learning about django |  | Worked with other team members and discussed the set up along with docker features
Week 4 : 9/27 - 10/04 | 12.5 | 10 | 2.5 | 0-Learnt how to write the user story and acceptance tests by following the format. Exploring how to use API for the project,Learning django. 1-Created 3 user stories for the project,broke down into tasks, wrote acceptance tests. 3- Installed the project application 5- continued discussion with team about git strategy, Discussed about presentaion and upload and download feature for the project. | 3.5 | 4.5 |  | 2 |  | 2.5 |  | 1) To work on the upload and download feature. 2) Learn more about API and the existing source code. 3) Create the slides for presentation.
Week 5: 10/04 - 10/11 | 10.5 | 7.5 | 3 | 0- Learning about Google drive features and Using API(Picker document) 1- Learning Testing techniques 3-made changes on Git to fix error in execution code. 5- Discussed with Team about integration of google Drive | 2.5 | 1 |  | 1 |  | 3
Week 6: 10/11- 10/18 | 11.5 | 8.5 | 3 | 0- Learning Refactoring and Testing 1- Created Slides for Presenataion 3-Practiced Implemeting UI and committed changes to document on git. 5-Discussed with team about presentation | 2 | 1 |  | 2.5 |  | 3
Week 7: 10/19 - 10/25 | 10 | 7 | 3 | 0- Reading about API 3-Was trying to implement making API call 5-Attended the meeting | 3 |  |  | 4 |  | 3
Week 8:11/01 - 11/07 |  | 6 | 3 | 0- Reading the documentation on google drive, could not understand it much. 5-Attended the meeting | 3 |  |  |  |  | 3
Week 9: 11/08 - 11/14 |  | 6 | 3 | 5-Attended meeting and Took meeting minutes 0- Started a tutorial on javascript | 3 |  |  |  |  | 3
Week 10: 11/15 - 11/21 |  | 7 | 3 | 0- Continued a tutorial on javascript 3- exploring on javascript applications 5-Attended the meeting | 2 |  |  | 2 |  | 3
Week 11: 11/22 - 11/28 |  |  |  | Did not attend the meeting and did not study this week due to travelling
Week 12: 11/29 - 12/05 |  | 6 | 2 | 0- going through the sample javascript codes and reading the documentation on google drive 5-Attended the meeting and disussed about the presenatation | 4 |  |  | 2
Week 13: 12/06 - 12/13 |  |  | 2.5 | Attended the meeting and discussed about the presentation.

## Nitish
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
Week 1 :09/06 - 09/13
Week 2 : 9/13 -9/20
Week 3 :9/20 - 9/27
Week 4 : 9/27 - 10/04
Week 5: 10/4 - 10/11
Week 6:10/11 - 10/18

## Dan Budris
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
9/6 - 9/13 |  | 3.75 |  | 0: started to review the project options and consider common technologies which we could apply to them installed the project management project locally, and reviwed its structure and make up. Attempted to re-create the backend nginx server setup. Built a base docker image to redeploy it as a development copy. 5: Created github repository and basic readme Created team slack channel Copied template docs to team folder Communicated updates to team channel Set up slack integration with Team 4 GitHub repository to track changes to the repo in slack | 180 |  |  |  |  | 45
9/13 -9/20 |  | 4.5 | 30 | 0: spent time looking over the codebase, started reading about Javascript, peer-to-peer video libraries, and the testing systems 5: built out our team, assigned roles, discussed merging teams, decided on a project goal 1: built out automated docker hub builds for project; on committ to github, new docker image is built and committed. Tested working. | 120 | 60 |  |  |  | 60
9/20 - 9/27 |  | 6.1667 | 90 | 0: spent significant ammount of time with the code base, and learning how Django administration and management works, so I could better understand the backend of the project 1: reviewed existing applications and considered the essential and non-essential features each has 5: worked with team members to help organize the production of the presentation 3: After learning about Django and significant trial and error, managed to create a default user through: direct database manipulation, and later Django setup command create_superuser; implemented a build step in the docker image which adds the superuser | 180 | 20 |  | 60 |  | 20
9/27 - 10/4 | 8 | 5 | 3 | 5: worked with team to set up subteams and break out tasks around different areas of the project 0: Read Django API documentation and played with the existing API functions and automatic documentaiton in order to understand how they work and where they route to/execute functions; did NodeJS exercises, and looked at the socket IO used by the chat application to better understand it, and used trial and error to determine core functions; 3: Set up a new automated docker build using the updated repository, and confirmed that it deploys a working version of the chat application 1: Worked my way through the chat application, and began generating user stories for bugs and improvements that we can make to the product | 2 | 1.5 |  | 1.5
10/4 - 10/11 | 8.75 | 6.75 | 2 | 0: Reviwed the HTLM, CSS, and Javascript static files for the communications application. Discovered the use of bootstrap and Font Awesome, and mixed use of in-line and external style sheets. Read about bootstrap framework and did exercises. Read about precedence of CSS cascades and the best practices around UI design and styling. 1: Wrote users stories for the creation of tool-tips and help documents to enhance the user experience of the communication application 3: Implemented tool tips for buttons in the chat application within the static CSS and HTML. Implemented a glyphicon video chat button in the message bar modal of the chat application with CSS and HTML. 5: Worked with team members to further clarify sub-team responsibilities, goals for iteration 1 presentation, and walk through the file system of the existing project. | 2.5 | 0.75 | 2 | 1 |  | 0.5
10/11 - 10/18 | 8.5 | 6.5 | 2 | 0: Read documentaiton and worked through the sample projects on WebRTC (real time communication library) creating a demo peer-to-peer app on my local machine (https://www.html5rocks.com/en/tutorials/webrtc/basics/#toc-simple) to better understand the required Node.js and Socket.io elements that we will be implementing. Read documentation around Cross Site Scripting vulnerabilities, their sources, and their remediation on OSWAP (https://www.owasp.org/index.php/Cross-site_Scripting_(XSS)) 1: Wrote user story for the bug behind the discovered cross-site scripting vulnerability. Began drawing class diagrams for help page and video conferencing application. 2: Designed the interface for a basic help page and the layout for help icons on the communication tool. 4: Ran through existing mocha JS tests and attempted to understand their application to Node.js, and worked on writing my own simple Mocha test stamples locally. Tested the input of the chat application with various inputs, and after inputing HTML tags discovered the cross-site scripting vulnerabilitiy. 5: Wrote a template for the iteration 1 presentation and shared it with the team. Wrote slides and slide content for recap of progress, review of the existing project and its context, the cross-site scripting vulnerability, and basic UI improvements (see presentation version history) Helped team members learn more about Git (fetch, branching, stash), and the workflow on how to use docker and git for fast local development. | 2.5 | 0.5 | 1 |  | 1 | 1.5
10/19 - 10/25 | 5.5 | 5 | 0.5 | 0: read about javascript and node; did an express js and node js tutorial 3: attempted to build a validator for the express app using a sanitizer middleware; this took a long time and did not yeild a lot of fruit. However, I managed to use a regext to do a stopgap sanitization which will work for that time | 2.5 |  |  | 2.5
11/01 - 11/07 | 5.5 | 5 | 0.5 | Travelling for work, so unable to attend team meetings. Met after class with George regarding the direction of the team. 3 - finished the implementation of the video chat integration into the 3 blueprints frontend. 2 - created sequence diagram for video chat feature internal messaging 1 - reviewed stories for iteration and made sure they reflected the work done, and closed/accepted stories; reviewed out current progress and created stories in pivotal tracker to reflect the remaining direction of the project 5 - created base presentation, inserted template slides and topics, and worked to ensure that the proper presenters created the slides in a timely and satisfactory manner. |  | 1 | 1 | 2 |  | 1
11/08 - 11/14 | 3 | 3 | 0 | Travelling for work, so unable to attend team meetings. 3 - continued to refine the front end integration; began working on the deployment process including troubleshooting the docker build and possible options for server deployment |  |  |  | 3
11/15 - 11/21 | 4 | 2 | 2 | 3 - given access to the deployment server, I worked through the existing deployment documentaiton and began the processes of deploying our updated app without breaking the existing deployment; this requires work with the nginx reverse proxy, ssl certificate, existin gunicorn setup, and the new Docker deployment setup. |  |  |  | 2
11/22 - 11/28 | 4 | 4 |  | 1 - reviewed and update stories around deployment 3 - updated nginx and ssl configurations to allow for the deployment of the existing app via docker |  | 1 |  | 3
11/29 - 12/5 |  | 5 | 2 | 3 - continued to troubleshot and work on the deployment to the production server; spent significant ammounts of time modifying the code and updating django and nginx in order to allow for proper pass-through between the production server and docker, and to allow for messaging over websocket over the public internet |  |  |  | 5
12/6 - 12/13 |  | 8.5 |  | 3 - modified the main app, migrating the JS and CSS in the seperate video chat index to the main JS, CSS, and Index files. This allowed for the video to be directly displayed in the browser, getting around the iframe cross-frame-origin issue with Chrome. Finished this and tested a successful deployment to the web server 5 - created slides for presentation and talking points for presentation 2 - created architectural diagrams for the presentation which outline the production application architecture and modifications |  |  | 1.5 | 5 |  | 2

## Jash Bhankharia
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
Week 1 :09/06 - 09/13 | 4 |  | 3.25 | 6- Project idea discussion. Coming up with different ideas and plan to make a score matrix out of it. |  | 0.25 |  |  |  | 0
Week 2 : 9/13 -9/20 | 4.5 |  | 0.5 | 6 - Shifting teams.Assigning roles. 1 - Understanding the new team project requirements. Finalising on the required, desirable and optional features. |  | 2.5 |  |  |  |  | 1.5
Week 3 :9/20 - 9/27 | 9 | 3 | 4 | 0 - Understanding code and work on SPPP. 6 - Installing the application on Virtual machine | 4 | [5 empty] | 1 | Teaching Github for people who have no experience with it. Make the previous project start working and understand the code even deeper.
Week 4 : 9/27 - 10/04 | 14 | 7 | 3 | 1: Created user case stories, tasks to be implemented and acceptance tests for them 3: Working on UI part of the application on Toolbar 5: Coordination in sub groups | 4 |  | 3 | 2 |  | 3
Week 5 : 10/5 - 10/11 | 8 | 3 | 5 | 0: Understanding the entire file structure for the different file types used in the communication application. Researched on how to use Bootstrap framework 1: Wrote users storiy for the creation of the toolbar on communication tool 5: Coordinating with sub groups | 4 | 2 |  |  |  | 2
Week 6 : 10/12 - 10/18 | 11 | 7 | 4 | 0: Learned about the WebRTC framework which we are going to use for developing the video chat application. 3: Helped in developing th WebRTC demo application for the presentation 6: Prepared for the presentation of Iteration 1 | 3 |  |  | 4 |  |  | 2
Week 7 : 10/19 - 10/25 | 6 | 3 | 3 | 3: Continued the implementation of the chat toolbar user story. Added the Logout functionality and tested successfully for the acceptance tests written for it |  |  |  | 3
Week 8 : 10/26 - 11/1 | 10 | 7 | 3 | 3: Completed writing code for change password and change profile information functionality 0: Understanding the different metrics than can be deduced. | 2 |  |  | 5
Week 9 : 11/2 - 11/8 | 7 | 4 | 3 | 6: Assisted in filling up the presentation slides with metrics and also trying to understand the different folder structures in the project for refactoring and finding out unused files 1: Updated the SPPP with new and revised requirements | 1 | [5 empty] | 3
Week 10 : 11/9 - 11/15 | 8 | 4 | 4 | 3: Started working on bugs in the application which were captured while testing. Fixed the team name validation issue where empty team names were getting created |  |  |  | 4
Week 12 : 11/16 - 11/22 | 10 | 6 | 4 | 3: Started working on the file upload bug. This bug was present in both requirements as well as communication tool. So I tried fixing it in requirements page first. Also working on the bug where the newest copy on Github was not working because of Google OAuth2 issues 4: Assisting the testing sub team with setting up the testing environment. |  |  |  | 4 | 2
Week 13 : 11/23 - 11/29 | 0 | 0 | 0 | Thanksgiving break.
Week 14 : 11/30 - 12/06 | 7 | 3 | 4 | 3: Continued working on previous bug and fixing it for the communication tool |  |  |  | 3
Week 15 : 12/07 - 12/13 | 5 | 2 | 3 | 6: Working on presentation. Filling up the bugs slides and the project management slides |  |  |  | 2

## Yergali Askarbayev
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1(09.06-09.13) | 2 | 6 |  | 0. tried to come up with some creative ideas to create project | 2 | [6 empty] | 0 | 8 hours
2 (09.13-09.20) |  | 12 | 0.5 | 0. seen some tutorials about python programming language and django framework 5. communication beetwen team members on slack and during the breaks and after class | 9 | [6 empty] | 0,1 | 8 hours
3(09.20-09.27) | 3 | 10 | 1.5 | 0. installed the existing project in my local project from github and runned the project in docker. 1. discussed requirements in meeting 5. communication beetwen team members in meeting, during the break and after class as well as on slack | 8 | 1 |  |  |  | 0.5 |  | 0,1, 2, 3 | 8 hours
4(09.27-10.04) | 1 | 12 | 2.5 | 0. seen tutorials about WebRTC and NodeJS from differenr sourses 1. tried make user stories by its requirements 2. discussed about the design with subgoups 3. came to the idea to read some posts regarding our project then decide the way of implementing the project 5. Created new project in github and tried to create own branch Seen some tutorial from Dan Budris and Mithin Shah | 8 | 1 | 0.5 | 0.5 |  | 1 |  | 2000-02-03 | 10 hours
5(10.04-10.11) | 5 | 12 | 2 | 2. designed the GUI for the video communication 3. started implementing the demo versio of video communication 5. discussed a way of implementing the video communication between sum team members |  |  | 1 | 11 |  |  |  |  | 10 hours
6(10.11-10.18) | 5 | 8 | 2 | 2. designed the GUI for peer to peer video communication 3. implemented the demo version of peer to peer video communication for interation 1 5. communiaction between team and sum team members about iteration 1 and implementation |  |  | 2 | 6 |  |  |  |  | 10 hours
7(10.18-10.25) |  | 10 | 2 | 2. designed an implementation of the individual texting feature between users in the communication tool 3. started an impelementation of the individual texting functions creating unique rooms under Spcket.IO API. 5. discussed different ways of implementing the individual texting feature. |  |  | 2 | 8 |  | 1 |  | 0, 2, 3, 5 | 10 hours
8(10.25-11.01) | 20 | 8 | 2 | 3. started an implementation of individual texting between two users 2. designed methods for individual texting 0. learned some techniques for testing and refactoring | 3 |  | 3 | 2 |  |  |  | 2, 3, 4, 5 | 10 hours
9(11.01-11.08) |  | 10 | 2 | 3. implemented basic individual texting feature in communication tool for users by creating models in django framework and creating new methods in js 2. adopted Restfull service(Rest Architecture) in communication tool for retriving and saving data between django and node.js 3. refactored some bad smells using Extract Methods, Extract variables and so.on |  |  | 5 | 5 |  |  |  | 2,3,4 | 10 hours
10(11.08-11.15) |  | 10 | 2 | 2. designed the sent time of messages in individual rooms and in groups 3. implemented the feature of messages' sent time by keeping track of time and saving them in database 5. disccused the main features of our project in group meating |  |  | 1 | 8 |  | 1 |  | 2, 3, 4, 5 | 10 hours
11(11.15-11.22) |  | 10 | 2 | 2. designed editing and deleting messages after sending 3. implemented editing messages creating functions in Node.js server side and updating data in database 5. discussed this implementation in group meatings |  |  | 1 | 9 |  |  |  | 2017-04-05 | 5 hours
12(11.22-11.29) | 8 | 4 | 2 | 4. tested all functions manually |  |  |  |  | 4 |  |  | 4 | 5 hours
13(11.29-12.06) | 15 | 3 | 2 | 3. fixed some bugs in features which was implemented by me |  |  |  | 3 |  |  |  | 4 | 5 hours
14(12.06-12.13) | 10 | 6 | 2 | 4. tested the application and fixed some bugs manually to prepare for final presentation | [6 empty] | 6

## Bakyt
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time hours | Total meeting time(minute) | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 week | 2.5 | 4 |  | 0 searchinf for the idea of group project and looked the old projects | 2
2 week |  | 4.5 | 30 | 0 learning diffeent git hub materials 2 worked in python 3 set up pivital tracker 3 set up docker 3 kitamatic in my computer 5 knew the groop members prefers in programming | 4
3 week |  | 6 | 30 | 0 analyze how the django works and impelemtn some git hub materials 4 analyze the existing projects 3 implemented the codes on python django | 3
4 week |  | 10 | 180

## Asli
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
Week 1(09/06-09/13) | 3.1 | 3.1 |  | 0 - Install github, django, slack, pivotaltracker 0 - Learning tools: Github, Docker 5 - Setting up Pivotal Tracker for Group 5 - Attend group meeting | 3 | 0 | 0 | 0 | 0 | 0.1 | 0 | Setup environment Some documentation works | 5
Week 2(09/13-09/20) | 6.5 | 6 | 0.5 | 0 - Setup environment 0 - Learning tools: Python, Django 5 - Attend group meeting | 6 | 0 | 0 | 0 | 0 | 0.5 | 0 | Continue learning python and django Understanding existing structure and code | 7
Week 3(09/20-09/27) | 6.5 | 3 | 3.5 | 0 - Figure out how to get code from GitHub and get environment set up 0 - Learn more about Python and Django, 5 - Attend group meeting | 3 | 0 | 0 | 0 | 0 | 3.5 | 0 | More understanding about existing code | 4
Week 4(09/27-10/04) | 8.2 | 4.2 | 4 | 4- Trying to understand and excute existing tests in the project 5 - Attend group meeting 6 - post-iteration review | 0 | 0 | 0 | 0 | 4 | 4 | 0.2 | Trying find bugs Creating user stories, estimate tasks and write acceptence test. | 7
Week 5(10/04-10/11) | 7.5 | 5.5 | 2 | 4- Trying to find some bugs with manuel tests 1 - Creating some user stories and acceptance tests 5 - Attend group meeting 1 - Adding user stories, estimate tasks and acceptance test to Pivotal Tracker | 0 | 3.5 | 0 | 0 | 2 | 2 | 0 | Preparing presentation Some research for finding bug | 4
Week 6(10/11-10/18) | 7.5 | 4.5 | 3 | 4- Trying to do find some bugs with manuel tests 6 - Preparing for the presentation | 0 | 0 | 0 | 0 | 1.5 | 3 | 3 | Working on the testing current system | 4
Week 7(10/18-10/25) | 7 | 7 |  | 0- Reading and learning more about Django and javascript and understanding existing code 4-Manuel testing | 4 | 0 | 0 | 3 | 0 | 0 | 0 |  | 7
Week 8(10/25-11/01) | 5 | 5 |  | 6- Understanding existing test environment(selenium testing and unit testing) | 0 | 0 | 0 | 0 | 0 | 0 | 5 |  | 6
Week 9(11/01-11/08) | 7,5 | 5,5 | 2 | 1- Added 2 user stories on Pivotal Tracker which two of them are about bugs 3- Working on bug/sameTeamName branch on github and fixed the problem. 6- this was my first comment so this helps me to learn git also 5 - Attend group meeting | 0 | 0,5 | 0 | 4 | 0 | 2 | 1 |  | 7
Week 10(11/08-11/15) | 9 | 7 | 2 | 0 - Learning about selenium framework 4- Create test cases for selenium test 0- set up selenium environment 5 - Attend group meeting | 5 | 0 | 0 | 0 | 2 | 2 | 0 | working on selenium | 7
Week 11(11/15-11/22) | 9 | 7 | 2 | 4- Start working on selenium test (doing some tests about previous functionality) and getting familiar with seleniium framework 4- Created detailed scenarios for this cases 5 - Attend group meeting | 0 | 0 | 0 | 0 | 7 | 2 | 0 | working on selenium | 8
Week 12(11/22-11/29) | 14 | 12 | 2 | 4- Start working on selenium test (doing some tests about our essential functionalities) (Some of them still not completed, so I worked on 4 selenium test cases) 0- Created detailed senarious for this cases | 0 | 0 | 0 | 0 | 12 | 2 | 0 | working on selenium | 10
Week 13(11/29-12/06) | 15 | 13 | 2 | 4- working on selenium test (doing some tests about rest ofour essential functionalities) 4- Created detailed scenarios for this cases 4 - Edit all scenarious to test case sheet 5 - Attend group meeting | 0 | 0 | 0 | 0 | 13 | 2 | 0 | working on selenium | 4
Week 14(12/06-12/13) | 6 | 4 | 2 | 0 - preparation presentation 5 - Attend group meeting 4 - committing all selenium test cases to github | 3 | 0 | 0 | 0 | 1 | 2 | 0

## George Goddard
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 (09/06/2017-09/12/2017) | 3 | 3 |  | 6 - trying to either form a team or join a team | [6 empty] | 3 | 6, 0 | 3
2 (09/13/2017-09/19/2017 | 4 | 3 | 1 | 6 - joined a team 0 - started looking at the code for the application 5 - discussed with team what we wanted to do | 2 |  |  |  |  | 1 | 1 | 0, 1 | 3
3 (09/20/2017-09/26/2017) | 7.5 | 3 | 4.5 | 0 - used docker image Dan made to explore some of the application 5 - during the meeting went over roles, filled out sppp and meeting minutes | 3 |  |  |  |  | 4.5 |  | 5, 0, 4 | 6
4 (09/27/2017-10/03/2017) | 13 | 9 | 4 | 0 - still learning about the application. The directories are not particularly well-organized or clear in their intent. Had Michael Song join us during our weekly meeting which was very helpful. Researched how to integrate with Google Drive for file upload/download/sharing. 5 - split into subteams to more effectively address features that we want to develop with smaller groups of people. Formed sub-team to address current file upload/download functionality and start planning Google Drive integration 1 - wrote user requirement stories for Google Drive integration and added them to pivotaltracker. | 6 | 3 |  |  |  | 4 |  | 0, 1, 2, 4, 5 | 10
5 (10/04/2017-10/10/2017) | 9 | 7 | 2 | 0 - continued to research integrating Google Drive into application. Continued to investigate the application. Got it running locally and was able to explore through interaction. 5 - communicated about documentation shared in Slack regarding our subteams development goals. Discussed how to properly branch in git and went over how to get the application to run locally with subteam members. 1 - revisted user stories to make any necessary changes | 6 | 1 |  |  |  | 2 |  | 2, 0, 3, 4, 5 | 10
6 (10/11/2017-10/17/2017) | 15 | 12 | 3 | 3 - implemented a dropdown menu button on the communication tool webpage to house Google Drive options. 4 - tried to run the unit and selenium tests for the entire application. It seems the testing of the application was left in an incomplete state. Some of the Django unit test reference packages which do not exist. Instructions are only partially helpful. Was finally able to get both the unit tests and the selenium tests to run after making modifications and installing packages. Around 51 tests were run, there was one failure and 10 errors because a port was already being used. I need to investigate what was causing those errors. 0 - read more documentation and examples related to integrating Google Drive with Django; specifically authentication methods including oauth2. Finally started to feel like I am understanding how the communication tool runs slightly. 2 - created a class diagram for the classes in the Django backend for the communication tool. Also analyzed the classed being used with the NodeJS backend and how they are stored persistently. Definitely helped with understanding the application more. 5 - spent more time discussing how we will try to integrate with Google Drive with members of my subteam. Discussed additional features we could attempt if we are successful with authentication, file upload, file download, and file sharing, including the Google Picker (file selection dialog) and RealTime implementation (multiple users able to modify the same document at the same time) | 4 |  | 2 | 6 | 1.5 | 1.5 |  | 2, 3, 4, 5 | 10
7 (10/18/2017-10/24/2017) | 14 | 11 | 3 | 1- started analyzing how to reduce the scope of user stories 0 - continued to learn about oauth2 and django 5 - took meeting minutes, communicated to sub-team about goals and timelines, discussed various topics with Dan 3 - started oauth2 implementation | 4 | 1 |  | 6 |  | 3 |  | 3, 5, 0, 1 | 8
8 (10/25/2017-10/31/2017) | 14 | 11 | 3 | 0 - continue learning django and google drive api 1 - continued effort on breaking down stories 3 - continued working on oath2 implementation 5 - weekly communication with sub-team and Dan | 4 | 1 |  | 6 |  | 3 |  | 1, 0, 3, 5 | 12
9 (11/01/2017-11/07/2017) | 22 | 19 | 3 | 0 - in addition to learning about oauth2, dived more into the google drive api and various languages it supports 1 - broke down stories into much more manageable portions 2 - much planning on google drive integration implemenation as a whole, mistaken assumptions that were made, and most effecient and effective way to progress 3 - completed working implementations of oauth2 and file download on the backend 5 - spent more time than usual with team communication. ran weekly meeting. delegated responsibilites. communicated goals for the presentation | 5 | 2 | 3 | 8 |  | 4 |  | 0, 1, 2, 3, 4, 5 | 8
10 (11/08/2017-11/14/2017) | 17 | 14 | 3 | 0 - keep reading documenation on google drive integration and authentication 3 - working on implementing google drive download functionality in the frontend 5- weekly team meeting | 4 |  |  | 8 |  | 5 |  | 3, 5, 0, 4 | 10
11 (11/15/2017-11/21/2017) | 17 | 14 | 3 | 0 - keep reading documenation on google drive integration and authentication 3 - working on implementing google picker and google drive upload file functionality in the frontend 5- weekly team meeting | 4 |  |  | 8 |  | 5 |  | 3, 5, 0, 4 | 10
12 (11/29/2017-12/05/2017) | 17 | 14 | 3 | 0 - keep reading documenation on google drive integration and authentication 3 - working on implementing google drive download functionality in the frontend 5- weekly team meeting 4 - discussed unit and selenium testing with teammates | 4 |  |  | 8 | 1 | 5 |  | 3, 5, 0, 4 | 10
13 (12/06/2017-12/12/2017) | 17 | 14 | 3 | 0 - keep reading documenation on google drive integration and authentication 3 - working on implementing google drive download functionality in the frontend 5- weekly team meeting | 4 |  |  | 8 |  | 5 |  | 3, 5, 0, 4 | 10