## Yuting zhang
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time

## Oindrilla Chatterjee
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
Week 1 :09/06 - 09/13 | 4 | 0.75 | 3.25 | 0- Learning how to Implement a scoring matrix to fix up a project idea 5- Forming of a Project Group,assignment of roles and responsibilities 6- Brainstorming project ideas ,Discussion of project ideas and finalisation of topic. Analysis of resources required for implementation | 0.5 | [5 empty] | 3.25 | 1. Discussion with the prof. regarding the project idea and scope. 2. Finalise the platform and technologies intended | 5
Week 2 : 9/13 -9/20 | 4.5 | 4 | 0.5 | 0: learning about existing project application , features and requirement analysis and decided a definite scope of Project 5: Joined team 4, assigned roles, discussed merging teams, decided on a project goal | 4 |  |  |  |  | 0.5 |  | 1. Setting up of a Git Repsitory 2. Running test cases on the Existing Application 3. Fill up the SPPP Documentation 4. Create the Iteration 0 Presentation | 2017-08-10
Week 3 :9/20 - 9/27 | 10 | 6.5 | 3.5 | 0: Learning version control using Git, setting up a github repository 2: Designed a work flow, a timeline gantt chart for the coming iterations 5: filling up of the SPPP, Meeting Minutes and Putting up of the Iteration 0 Presentaion slides | 4.5 |  | 2 |  |  | 3.5 |  | 1. Chalk out a Quality Assurance Plan 2. Running test cases | 10
Week 4 : 9/27 - 10/04

## Shaurya Muttreja
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
9/13 - 9/20 |  | 1.5 |  | 5-Team collaboration and role discussion for project signup sheet 6-Joined the team
9/20 - 9/27 |  | 3 | 1 | 0-Project ideas were discussed in detail 1-Requirements of technology discussed (Python django, SQLlite) 3-Installed exsisting project locally using docker. (Instruction given from Dan B) 5-Communication on slack channel about potential screen share frameworks(WebRTC) 6-Merge of team 2 and 4

## Jash Bhankharia
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
Week 1 :09/06 - 09/13 | 4 |  | 3.25 | 6- Project idea discussion. Coming up with different ideas and plan to make a score matrix out of it. |  | 0.25 |  |  |  | 0
Week 2 : 9/13 -9/20 | 4.5 |  | 0.5 | 6 - Shifting teams.Assigning roles. 1 - Understanding the new team project requirements. Finalising on the required, desirable and optional features. |  | 2.5 |  |  |  |  | 1.5
Week 3 :9/20 - 9/27 | 7 | 3 | 4 | 0 - Understanding code and work on SPPP. 6 - Installing the application on Virtual machine | 4 | [5 empty] | 1 | Teaching Github for people who have no experience with it. Make the previous project start working and understand the code even deeper.

## Mithil Shah
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/18-09/24 |  |  | 4hrs |  | 180
Review the platform the project idea could be built on. Laid down the coding guidelines. Understood and discussed possible ideas and features on the project going forward and laid down iteration ideas.
[5 empty] | Set the project up to run and learned the docker version of it. |  |  |  |  | Set & discussed the version control guidelines.
Shared documentation of version control documentation with team

## Apurva
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | 210 | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
Week1 (09/06/2017- 09/10/2017) |  |  |  |  | Exploring on different ideas for project. And trying to explore more tools required to have a real world application.
Week 2(09/13-09/17) |  | 3 |  |  | Installed the project and reviewed its details and also attended a session to learn more about Git
9/20 - 9/27 |  | 90 | 160 |  | 0- spent time to get familiar with the docker | 1Looked into the already existing features and code.Tried to make the changes to make the login page work. |  | Started learning about django |  | Worked with other team members and discussed the set up along with docker features

## Dan Budris
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
9/6 - 9/13 |  | 3.75 |  | 0: started to review the project options and consider common technologies which we could apply to them installed the project management project locally, and reviwed its structure and make up. Attempted to re-create the backend nginx server setup. Built a base docker image to redeploy it as a development copy. 5: Created github repository and basic readme Created team slack channel Copied template docs to team folder Communicated updates to team channel Set up slack integration with Team 4 GitHub repository to track changes to the repo in slack | 180 |  |  |  |  | 45
9/13 -9/20 |  | 4.5 | 30 | 0: spent time looking over the codebase, started reading about Javascript, peer-to-peer video libraries, and the testing systems 5: built out our team, assigned roles, discussed merging teams, decided on a project goal 1: built out automated docker hub builds for project; on committ to github, new docker image is built and committed. Tested working. | 120 | 60 |  |  |  | 60
9/20 - 9/27 |  | 6.1667 | 90 | 0: spent significant ammount of time with the code base, and learning how Django administration and management works, so I could better understand the backend of the project 1: reviewed existing applications and considered the essential and non-essential features each has 5: worked with team members to help organize the production of the presentation 3: After learning about Django and significant trial and error, managed to create a default user through: direct database manipulation, and later Django setup command create_superuser; implemented a build step in the docker image which adds the superuser | 180 | 20 |  | 60 |  | 20
0
0
0
0
0
0
0

## Yergali Askarbayev
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1(09.06-09.13) | 2 hours | 6 hours |  | 0. tried to come up with some creative ideas to create project | 2 hours | [6 empty] | 0 | 8 hours
2 (09.13-09.20) |  | 12 hours | 30 | 0. seen some tutorials about python programming language and django framework 5. communication beetwen team members on slack and during the breaks and after class | 9hours | [6 empty] | 0,1 | 8 hours
3(09.20-09.27) | 3 hours | 10 hours | 90 | 0. installed the existing project in my local project from github and runned the project in docker. 1. discussed requirements in meeting 5. communication beetwen team members in meeting, during the break and after class as well as on slack | 4 hours | [6 empty] | 0,1, 2, 3 | 8 hours

## Bakyt
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 week | 2.5 | 4 |  | 0 searchinf for the idea of group project and looked the old projects | 2
2 week |  | 4.5 | 30 | 0 learning diffeent git hub materials 2 worked in python 3 set up pivital tracker 3 set up docker 3 kitamatic in my computer 5 knew the groop members prefers in programming | 4
3 week |  | 6 | 30 | 0 analyze how the django works and impelemtn some git hub materials 4 analyze the existing projects 3 implemented the codes on python django | 3

## Asli
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time

## George Goddard
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 (09/06/2017-09/12/2017) | 3 | 3 |  | 6 - trying to either form a team or join a team | [6 empty] | 3 | 6, 0 | 3
2 (09/13/2017-09/19/2017 | 4 | 3 | 1 | 6 - joined a team 0 - started looking at the code for the application 5 - discussed with team what we wanted to do | 2 |  |  |  |  | 1 | 1 | 0, 1 | 3
3 (09/20/2017-09/26/2017) | 7.5 | 3 | 4.5 | 0 - used docker image Dan made to explore some of the application 5 - during the meeting went over roles, filled out sppp and meeting minutes | 3 |  |  |  |  | 4.5 |  | 5, 0, 4 | 6